## Sprint Plan
SN# | Story# | Description | Story Point | Actual SP | Sprint# | Developer | Status | QA | Issues | Sprint # | Start Date | End Date | Days
1 | HRM001_Dashboard | Dashboard | 3 |  | Sprint-1 | Ahmed | Done | Pending |  | Sprint-1 | 2018-08-12 | 2018-08-26 | 14
2 | HRM002_ReportingMethod |  | 3 |  | Sprint-2 | Ahmed | Done | Pending |  | Sprint-2 | 2018-08-27 | 2018-09-10 | 14
3 | HRM003_TerminationReason |  | 3 |  | Sprint-2 | Ahmed | Done | Pending |  | Sprint-3 | 2018-09-11 | 2018-09-25 | 14
4 | Testing all links |  | 4 |  | Sprint-2 | Zoha | Done | Done |  | Sprint-4 | 2018-09-26 | 2018-10-10 | 14
5 | DB Update not working | DB Change not reflecting | 1 |  | Sprint-2 | Shahid | Done | Pending |  | Sprint-5 | 2018-10-11 | 2018-10-25 | 14
6 | HRM004_Holidays | Service Details | 0.5 |  | Sprint-3 | Zoha | Pending | Pending | Spill Over | Sprint-IP | 2018-10-26 | 2018-11-09 | 14
7 | HRM005_Working Days | Service Details | 0.5 |  | Sprint-3 | Zoha | Done | Pending
8 |  | Company Work Week | 0.5 |  | Sprint-3 | Ahmed | Pending | Pending
9 | Leave Entitlement Screen | Existing Screen | 1 |  | Sprint-3 | Saleem | Pending | Pending
10 | HRM12-Leave-Period_Assigned |  | 0.5 |  | Sprint-3 | Ahmed | Pending | Pending
11 | HRM11-Asset-Managment_Assigned | Add Vender | 0.5 |  | Sprint-3 | Zoha | Done | Pending
12 | HRM11-Asset-Managment_Assigned | Asset Mangement- Category | 0.5 |  | Sprint-3 | Zoha | Done | Pending
Formulas:
End Date = [Start Date]+14
Start Date = [Start Date, row above]+14+1

## List
Status List
Pending
Done
On-Hold
In-Progress